## ProjectDetails
Project Name: | Ambyint.ToDoApplication
References: | Project Plan
Introduction: | To perform comprehensive quality assurance on a simple To-Do application, designated as the Application Under Test (AUT), utilizing any testing tools like Selenium or Cypress
Test Items: | Test application on windows and macOS environment.
Features to be tested ( Scope In ): | Add, Edit, Mark and Delete
Feature not to be tested ( Scope Out ) : | NA
Approach : | Agile methodology.
Pass/Fail criteria : | Pass percentage should be approx. 95% without any critical bug.
Suspension Criteria : | In case of non functionality of any major functionality, we will stop testing.
Test Deliverables : | Test Cases, Test summary report
Environment : | List of hardware and software required to test: | Browser /OS | Win 10 | Mac OS X
|  | Chrome 113 | Pass | Pass
|  | Safari 16.3 | Pass | Pass
Business Priority : | Priority describes the importance and order in which a bug should be fixed. The available priorities are:
4 - Low
3 - Medium
2 - High
1 - Critical
Severity : | Severity describes the impact of bugs. Defects will be classified as such by the Project Manager:
Test Scenarios, Test cases : | Please follow next excel sheet 2 named TestData

## TestData
Test Scenario | Test Scenario Desc | Test Case ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Results | Actual Results | Pass/Fail | Priority | Severity
TS001 | Check adding functionality | TC001 | Verify when case sensitive alpha numeric characters with space and special characters are added, they are displayed correctly on ToDo list. | Windows 10; Chrome | 1. Open index.html 2. Enter Test data and hit Enter 3. Verify if the added data is displayed in To-Do List | 1. 123456789/*-+.!@#$%^&*()_+- ` 2. Do Grocery shopping | Input is added at the end of the list 1. 123456789/*-+.!@#$%^&*()_+- ` 2. Do Grocery shopping | As expected | Pass
|  | TC002 | Verify when a user enters spaces at the beginning, in between, or at the end, extra spaces are trimmed. | Windows 10; Chrome | 1. Open index.html 2. Enter Test data and hit Enter 3. Verify if the added data is corrected | 1. hi123! 2. hi123! hi123@ | 1. hi123! 2. hi123! hi123@ | As expected | Pass
|  | TC003 | Check if any max length is set, for example 140 | Windows 10; Chrome | 1. Open index.html 2. Enter Test data and hit Enter 3. Verify if the added data is accepted or not | 1. a.repeat(140) | Prompt or error for maximum length. Text box should have a max length criteria set up for the input. | Text box is accepting any length of the input | Fail | 3 | 3
|  | TC004 | Verify if duplicate inputs are allowed | Windows 10; Chrome | 1. open index.html 2. Enter Test data and hit Enter 3. Check the ToDo list window for duplicates | 1. Buy Grocery 2. Buy Grocery | Duplicate warning and only 1 ToDo list on display | 1. Buy Grocery 2. Buy Grocery | Fail | 1 | 2
TS002 | Check editing functionality | TC005 | Verify when user tries to edit an existing ToDo list, it is edited and it shows new updated list | Windows 10; Chrome | 1. open index.html 2. Enter a ToDo list Data and hit Enter 3. Click on the 3 dots for 'Change Tires.' > Edit : add "All 4" et the end 4. Edit it to: Buy Grocery for 1 week | 1. Buy Grocery 2. Running @ Treadmill 3. Change Tires. 4. Pay credit card bill 5. Enroll in a course 6. Finish python promming tutorial 7. Optimize scripts 8. Finish Ambyint project 9. Talk to manager about website 10. File> Open > Edit > Save | User should be able to edit it and new list should be 'Change Tires.All 4' without changing its sequence order | As expected | Pass
TS003 | Checking Marking/Completed functionality | TC006 | Verify when the user marks single added to-do list, it is crossed from the list and it is shown in the completed tab and not in pending task | Windows 10; Chrome | 1. open index.html 2. Enter a ToDo list Data and hit Enter 3. Click on the same to-do list 4. Check completed list | 1. Buy Grocery | 1. To-do list should be crossed of in All tab 2. Same to-do list should be visible on Completed Tab 3. it should not be in the Pending task tab | As expected | Pass
|  | TC007 | Verify when the user marks any to-do list from a list of todo list, it is crossed from the list and it is shown in the completed tab | Windows 10; Chrome | 1. open index.html 2. Enter a ToDo list Data and hit Enter 3. Click on the odd to-do list 4. Check completed list tab, pending tasks tab and all tasks tab | 1. Buy Grocery 2. Running @ Treadmill 3. Change Tires. 4. Pay credit card bill 5. Enroll in a course 6. Finish python promming tutorial 7. Optimize scripts 8. Finish Ambyint project 9. Talk to manager about website architecture 10. File> Open > Edit > Save | 1. Marked tab should be crossed in all tasks tab 2. Marked tab should be visible on Completed tasks tab 3. UnMarked tab should be visible on Pending tasks tab | As expected | Pass
TS004 | Checking deleting to-do list functionality | TC008 | Verify when the user deletes single added to-do list, the record is deleted | Windows 10; Chrome | 1. open index.html 2. Enter a ToDo list Data and hit Enter 3. Click on the 3 dots > Delete | 1. Buy Grocery | Item should be deleted from the Todo list | As expected | Pass
|  | TC009 | Verify when the user deletes single added to-do list from a large list, the respective record is deleted | Windows 10; Chrome | 1. open index.html 2. Enter a ToDo list Data and hit Enter 3. Click on the 3 dots for 1st list item > Delete | 1. Grocery shopping 2. Running @ Treadmill 3. Driving 100 kms. 4. Pay credit card bill 5. Enroll in a course 6. Finish python promming tutorial 7. Optimize scripts 8. Finish Ambyint project 9. Talk to manager about website architecture 10. File> Open > Edit > Save | 1. Respectetive item should be deleted | Wronk item list is getting deleted from the list | Fail | 1 | 1